## Phase 1
Task
Phase 1
Authentication & Authorization
Login
with email
with Google plus
with Facebook
Company Registration
with email
Account / User Management
User
Create/Update/Delete
Reset Password
Role
System Admin
Company Admin
Company Staff
Administrative Module
| Update Company Profile |  | Upload company logo and some general information of the company such as some breif infromation about company, address, contact information, trade
Project Management
Project
Project List
Create / Update
Trade or Checklist
Trade/ Checklist List
Create/ Update/ Delete
| Assign |  |  | Assignment Module
Company Staff
Notification and Alert
General Notification
System Admin Module & Backend process
| Activity Log |  | All the activity done by user must be record and save in DB
Others
Dashboard

## Phase 2
Task
Phase 2
Authentication & Authorization
Company Registration
with Google plus
with Facebook
Forget Password
Account / User Management
User
Search user
Invite user
Role
Safety Consultant
Safety Auditor
Project Management
Project
Mapping Trade
|  | Ceate Project with Wizards | For example, if the user choose bizsafe level 3, all related checklist are created automatically for user
Trade or Checklist
Ceate Project with Wizards
Assign
Other Company
Safety Officer
Audtior
Project / trade / checklist
Approved
Reject
Repository Management
File Managment
Upload File
Overwrite File
Delete File
Version Control
| Plan Management |  | For example, if bizsafe level 3, save all related checklist
| Trade Management |  | Save all related checklist for each trade
Template File
Publish
Duplicate
System Admin Module & Backend process
Approve / Reject Company Registration
Maintanence Script
Delete data marked as 'DEL' status
Delete Isolated data
Backup / Restore
Notification and Alert
Email notification
Worker Management
Worker Information
Create/ Update / Delete
Upload certificate
Notify expired certificate
Training Record Management |  |  |  | requirement gathering stage
Report Module |  |  |  | need calrification

## Full Schedule
Task |  |  | Phase | Comments
Authentication & Authorization
| Login |  | Review 1 | Migrate from old system
with email
with Google plus
with Facebook
Company Registration
|  | with email | Review 1
|  | with Google plus | Review 2
|  | with Facebook | Review 2
| Forget Password |  | Review 1
Account / User Management
User
|  | Create/Update/Delete | Review 1
|  | Reset Password | Review 1
|  | Search user | Review 1
|  | Invite user | Review 2
| Role |  |  | Relate to all the module
|  | System Admin | Review 1
|  | Company Admin | Review 1
|  | Company Staff | Review 1
|  | Safety Consultant | Review 2
|  | Safety Auditor | Review 2
Administrative Module
| Update Company Profile |  | Review 1 | Upload company logo and some general information of the company such as some breif infromation about company, address, contact information, trade
Project Management
Project
|  | Project List | Review 1
|  | Create / Update | Review 1
|  | Mapping Trade | Review 2
|  | Ceate Project with Wizards | Review 2 | For example, if the user choose bizsafe level 3, all related checklist are created automatically for user
Trade or Checklist
|  | Trade/ Checklist List | Review 1
|  | Create/ Update/ Delete | Review 1
|  | Ceate Project with Wizards | Review 2
| Assign |  |  | Assignment Module
|  | Company Staff | Review 1
|  | Other Company | Review 1
|  | Safety Officer | Review 2
|  | Audtior | Review 2
| Project / trade / checklist |  |  | Workflow management
|  | Approved | Review 1
|  | Reject | Review 1
|  | Track | Review 1
Repository Management
| File Managment |  | Review 1
Upload File
Overwrite File
Delete File
| Version Control |  | Review 2
| Plan Management |  | Review 2 | For example, if bizsafe level 3, save all related checklist | requirement gathering stage
| Trade Management |  | Review 2 | save all related checklist for each trade | requirement gathering stage
| Template File |  | Review 2 |  | requirement gathering stage
Publish
Duplicate
Notification and Alert
| General Notification |  | Review 1
| Email notification |  | Review 2
Others
| Dashboard |  | Review 1
System Admin Module & Backend process
| Activity Log |  | Review 1 | All the activity done by user must be record and save in DB
| Approve / Reject Company Registration |  | Review 2
| Maintanence Script |  | Review 2
Delete data marked as 'DEL' status
Delete Isolated data
| Backup / Restore |  | Review 2
Worker Management
| Worker Information |  | Review 2
Create/ Update / Delete
Upload certificate
Notify expired certificate
Training Record Management |  |  |  |  | requirement gathering stage
Report Module |  |  |  |  | need calrification

## Construction Trades
Trade | Description
Boilermaker
Craftsman
Carpet layer
Dredger
Electrician
PowerLine Technicians
Elevator mechanic
Fencer
Glazier
Heavy equipment operator
Insulation
Ironworker
Laborer
Landscaper
Mason
Millwright
House painter and decorator
Pile driver
Plasterer
Plumber
Pipefitter
Sheet metal worker
Fire sprinkler
Steel fixer
Truck driver
Waterproofer
Welder